## Hoja1
ID | Risk type | Description | Probability | Probability value | Effect | Effect value | Priority | Solution
Rk-001 | Project | One of the team member gets sick and is not able to finish his/her assignments. | Low | 2 | Serious | 2 | 16 | The schedule of the activities should be flexible enough to reassign the remaining tasks among the other members. |  | Project
Rk-002 | Project | One of the team members has personal issues that do not allow him/her to work in the project. | Low | 2 | Serious | 2 | 16 | The schedule of the activities should be flexible enough to reassign the remaining tasks among the other members. |  | Technical
Rk-003 | Project | It is impossible or very difficult to communicate with the customer and stakeholders to get important information. | Very low | 1 | Critical | 3 | 12 | Fix proper communication channels and conditions with both customer and stakeholders. |  | Business
Rk-004 | Project | The customer requests changes in the requirements that strongly modifies the structure of the product to be delivered. | Very low | 1 | Catastrophic | 4 | 16 | Requirements have to be frozen in agreement with the customer, before the implemetation phase. | Insignificant
Rk-005 | Project | The team misunderstands the requirements set provided by the customer. | Low | 2 | Catastrophic | 4 | 32 | Create mechanisms to validate the perspective that the team members have about the requirements. | Serious | Very low
Rk-006 | Project | One of the team member quits. | Very low | 1 | Catastrophic | 4 | 16 | The schedule of the activities should be flexible enough to reassign the remaining tasks among the other members. | Critical | Low
Rk-007 | Technical | The team members do not have enough time to complete the project. | High | 4 | Catastrophic | 4 | 64 | The schedule plan should take into account the potential additional work that the team members will have to develop along the semester. Eventual negotiations with the teacher can be considered. | Catastrophic | Medium
Rk-008 | Technical | The development team has not enough skills to use the tools to implement the software. | Low | 2 | Critical | 3 | 24 | The selection of the development languages and tools must take into account the skills of the members. |  | High
Rk-009 | Technical | The physical equipment is damaged. | Very low | 1 | Catastrophic | 4 | 16 | Have backup of the information stored in the devices. Buy new equipment to replace the damaged ones. |  | Very high
Rk-010 | Technical | The software application is affected by a security problems. | Low | 2 | Critical | 3 | 24 | Ensure the security of the system during the development phase.
Rk-011 | Technical | The components of the system cannot communicate each other because of connection problems. | Medium | 3 | Serious | 2 | 24 | Have alternative communication ways in case of failure.
Rk-012 | Technical | The external systems do not behave as expected (the interfaces that they provide are no longer working properly). | High | 4 | Serious | 2 | 32 | Find a different provider of the service or change the implementation to adapt to the new interfaces.
Rk-013 | Business | The calculation of the fee is not actually fair either for passenger or taxi drivers. | High | 4 | Serious | 2 | 32 | The calculation of the fee should be easily modifiable.
Rk-014 | Business | The allocation of an available taxi driver for the passengers is taking too much time. | Medium | 3 | Serious | 2 | 24 | Load tests should be performed to ensure an optimal response. The implementation has to be done with efficient algorithms.